NOTES OF A MEETING OF THE ADDINGHAM NEIGHBOURHOOD PLAN FORUM HELD AT MOUNT HERMON ON FRIDAY 2 FEBRUARY 2018

Present: 	Parish Council: Cllr Appleyard (Chairman), and J Markham (Clerk)

Civic Society:  J Robinson, M Keeble, J Hindle (Environment Group)

Village Residents: A Taylor, M Wood, K Appleyard

Apologies:  	Parish Council: Cllrs Naylor and Tennant

Civic Society: R Walton, K Birch

Kirkwells: M Wellock

- Notes of Meeting held on 7 December 2017

Noted.    The request for data requested from Bradford officers, eg to enable verification of numbers of houses generated from “windfall” developments, had been followed up, but a reply had yet to be received.

- Draft Preferred Options Neighbourhood Plan

The draft Plan, circulated in advance of the meeting, was discussed in detail and comments and queries were agreed for referral back to Kirkwells.

The final green space assessments, now included in the draft, were noted.

- Consultation on Preferred Options Draft Plan

Arrangements for the presentation display and open event, to take place over two days (Friday afternoon/evening and Saturday morning on 9th and 10th March) were discussed, and would be finalised at an informal meeting of the Forum volunteer members to be held on 28 February.

It was noted that the event was to be publicised in the forthcoming village newsletter, distributed to every household and business in the village.  A draft poster, tabled at the meeting, was discussed, and it was agreed that an alternative would be prepared by the Clerk for review and comment outside the meeting.

Further guidance on organising the consultation, including the most appropriate means of handling consultation feedback, had been requested from Kirkwells, and would be circulated outside the meeting.

- Next Meeting

Date for next meeting to be confirmed.