ADDINGHAM NEIGHBOURHOOD PLAN SITE ALLOCATIONS (SHLAA3 Methodology?)

- Following the workshop session on 3rd March 2017 this is a short note to set out the proposed process for the Addingham Neighbourhood Plan allocation of sites for housing. The key steps are identified along with key actions.

- The methodology set out below is broadly based on the CBMDC Issues and Options Site Assessment Methodology.

- Work up and agree site appraisal template and scoring based on the work already completed (Appendix 1).

- Scope sites for inclusion in study within the Village Boundary – all Green Belt sites are excluded (see note 11). Initial sites will include SHLAA3 2015 potential sites without planning permission  (flesh colour shading on Figure 1); sites identified by Civic Society; and any other known sites within the Village Boundary.

- Ask CBMDC for comments on 3 and 4. Consult for two to three weeks.

- Revise 2 and 3 in light of response at 5.

- Publish final versions of 2 and 3.

- Run “call for sites” only seeking sites not in the Green Belt.

- Appraisal of sites identified at 4 and 8.

- Publish results of appraisal at same time as publishing Draft Plan for informal consultation.

- If you do wish to look at Green Belt sites my suggestion would be to assess these against a separate appraisal process to assess how they perform against the five purposes of Green Belt. The final site appraisal and scoring published at 7 could then be used to assess any sites considered to no longer perform a suitable Green Belt function. This work would have to identify separate parcels of Green Belt land adjoin the complete Village Boundary (see http://www.pendle.gov.uk/downloads/download/2985/green_belt_assessment for an example from Pendle).

Figure 1. SHLAA3 2015

Appendix 1

SITE REFERENCE/LOCATION

BASIC SITE INFORMATION

| Site Name |  |
| --- | --- |
| BMDC SHLAA Ref |  |
| Site Address |  |
| Site Area (hectares) |  |
| Flood Zone (rivers & seas) |  |
| Flood Zone (surface water) |  |
| Site capacity (no. units) |  |
| Existing Use |  |
| Brownfield/Greenfield % |  |
| RUDP Village Green Space |  |
| Site located in Conservation Area |  |
| Site located in Green Belt |  |
| Site Description |  |

(A)  INITIAL SCREENING OUT OF SITES (ref BMDC  Stage 3)

| AVAILABILITY: The land is available for development (i.e. the landowner/developer is willing to sell/develop the land). (NB If in the BMDC SHLAA then it is assumed available unless it is known otherwise) | Yes/No/Unknown |
| --- | --- |
| SITE WHOLLY IN FLOOD ZONE 3b | Yes/No/Unknown |

(B) GROUPING & PRIORITISING REMAINING SITES (ref BMDC Stage 4)

Core Strategic Policy SC5

| Priority 1: Re-use of deliverable & developable previously developed land & buildings within settlements |  |
| --- | --- |
| Priority 2: Mixed green field/brownfield sites within settlements |  |
| Priority 3: Greenfield sites within settlements |  |
| Priority 4: Local green belt releases to the built up areas of settlements |  |

(C)   BRADFORD COUNCIL SITE ASSESSMENT METHODOLOGY – TECHNICAL APPRAISAL OF SITES – SUITABILITY [ref BMDC Stage 5]

|  | RED | AMBER 1 | AMBER 2 | GREEN | NOTES |
| --- | --- | --- | --- | --- | --- |
| HIGHWAYS/ACCESS |  |  |  |  |  |
| DRAINAGE/FLOOD RISK |  |  |  |  |  |
| HERITAGE IMPACT |  |  |  |  |  |
| WILDLIFE/ECOLOGICAL IMPACT |  |  |  |  |  |
| TREES/WOODLANDS |  |  |  |  |  |
| LANDSCAPE IMPACT |  |  |  |  |  |
| OPEN SPACE/GREEN INFRASTRUCTURE |  |  |  |  |  |

(C)  NATIONAL AND LOCAL POLICIES/PRIORITIES -  NPPF AND BRADFORD CORE STRATEGY

| POLICY/PRIORITY |  | NOTES |
| --- | --- | --- |
| Encourage/prioritise use of Previously Developed Land NPPF/ BMDC Policy SC5 (use this policy to sift sites) |  |  |
| Protect Green Belt (unless “exceptional circumstances”) NPPF/BMDC Policy SC7 |  |  |
| Prioritise use of land with least environmental/amenity value ? |  |  |
| Protect the South Pennine Moors SPA & SCA & their zone of influence (Zone B) BMDC Policy SC8 |  |  |

(D)  ACHIEVABILITY

- Physical Constraints

- Current Policy Constraints (eg would require Greenbelt Release/ Village Green Space designation)

- Development Viability

- Timeframe for development

CONCLUSION

DEVELOPMENT ACCEPTABLE ?                                               N0. OF DWELLINGS

YES   □  NO   □

Sites AD/002 part only, AD/003, AD/004 part only, AD/011 and AD/016